## Sheet1
Sr No | Task Number | Story Number | Description | Sign Off | DevSprint | Sprint | Is Automate | Owner | Priority | Sprint Start Date | Sprint End Date
1 | CP-616 | CP-530 | Add FAQ topic | Yes |  |  | Yes
2 | CP-638 | CP-554 | Create Ticket landing page | Yes |  |  | Yes
3 | CP-642 | CP-545 | Search merchant profile by user mobile number | Yes |  |  | Yes
4 | CP-651 | CP-546 | Edit FAQ topic | Yes |  |  | Yes
5 | CP-652 | CP-518 | Delete FAQ topic | Yes |  |  | Yes
6 | CP-655 | CP-531 | Add FAQ article | Yes |  |  | Yes
7 | CP-653 | CP-547 | Edit FAQ article |  |  |  | Yes
8 | CP-657 | CP-657 | Delete FAQ article |  |  |  | Yes | Wrong number
9 | CP-764 | CP-701 | Reply Merchant CS Ticket - Automatic Self Assignement | Yes |  |  | Yes
10 | CP-766 | CP-677 | View Merchant CS Ticket Details - No Business Profile Linked | Yes |  |  | Yes
11 | CP-649 | CP-560 | View Merchant CS Ticket List | PO review |  |  | Yes
12 | CP-699 | CP-544 | Search merchant profile by user email | Yes |  |  | Yes
13 | CP-740 | CP-545 | Search merchant profile by combinations | Blocked |  |  | Blocked
14 | CP-765 | CP-611 | Send internal note | Yes |  |  | Yes
15 | CP-698 | CP-541 | Reply Merchant CS Ticket. | Yes
16 | CP-793 | CP-599 | Automation testing for Confirm Menu Display and Name | Completed |  | sprint 7.1 |  | VC | 7 | 22/08/2018 | 2018-05-09
17 | CP-792 | CP-524 | Automation testing for Create Monetary Adjustment Application | Blocked |  | sprint 7.1 |  | VC | 1 | 22/08/2018 | 2018-05-09
18 | CP-785 | CP-561 | Automation testing for ordering update for FAQ article | Completed |  | sprint 7.1 |  | VC | 6 | 22/08/2018 | 2018-05-09
19 | CP-784 | CP-559 | Automation testing for ordering update for FAQ topic. | Completed |  | sprint 7.1 |  | VC | 5 | 22/08/2018 | 2018-05-09
20 | CP-787 | CP-608 | Automation testing for edit ticket details | Completed |  | sprint 7.1 |  | VC | 4 | 22/08/2018 | 2018-05-09
21 | CP-786 | CP-711 | Automation testing for view Ticket Details - Conversation History Status | Completed |  | sprint 7.1 |  | VC | 3 | 22/08/2018 | 2018-05-09
22 | CP-808 | CP-609 | Automation testing for View Merchant CS Ticket Details | Completed |  | sprint 7.1 |  | VC | 2 | 22/08/2018 | 2018-05-09
23 | CP-838 | CP-697 | Automation testing for Private / Public Ticket Type | Backlog | CS&O Inc 7 - sprint 1
24 | CP-837 | CP-661 | Automation testing Encounter errors when approving HKID edits | Backlog | CS&O Inc 7 - sprint 1
25 | CP-836 | CP-598 | Automation testing for View / Approve Application | Backlog | CS&O Inc 7 - sprint 1
26 | CP-835 | CP-627 | Automation testing for view merchant profile | Backlog | CS&O Inc 7 - sprint 1
27 | CP-834 | CP-525 | Automation testing for Create Cashout Reversal Application | Backlog | CS&O Inc 7 - sprint 1
| CP-865 | CP-593 | Automation testing for Switch Tabs on FAQ Management Landing Page | Backlog | CS&O Inc 7 - sprint 1
23 | CP-975 | CP-636 | Search merchant profile by business name | Backlog |  | sprint 7.2 |  | VC | 1 | 2018-05-09 | 18/9/2018
24 | CP-976 | CP-760 | Amend User Status (Active, Suspended) | Backlog |  | Sprint 7.2 |  | VC |  | 2018-05-09 | 18/9/2018
Sr No | Task Number | Story Number | Description | DevStatus | Autostatus | Sprint | Is Automate | Owner | Priority | Sprint Start Date | Sprint End Date
| CP-1061 | CP-789 | Create Work Group | ReadyForBuild | Draft script is ready | Sprint 7.3
| CP-1062 | CP-790 | Update Work Group Entitlements | ReadyForBuild | Draft script is ready | Sprint 7.3
| CP-1063 | CP-791 | Deactivate / Reactivate Work Group | ReadyForBuild | Draft script is ready | Sprint 7.3
| CP-1064 | CP-953 | Build functions allowed to be entitled to each work group | ReadyForBuild |  | Sprint 7.3
| CP-1069 | CP-1043 | Pressing "Enter" to Search | InBuild | Executed on CI environment | Sprint 7.3 | Yes
| CP-1071 | CP-963 | Replace Group Level 1 & 2 with Work Group in System User Page | ReadyForBuild | Draft script is ready | Sprint 7.3 | Yes
| CP-1072 | CP-968 | Modify "assign to" drop-down list mapping to active work group only | ReadyForBuild |  | Sprint 7.3 | Yes
| CP-1074 | CP-1046 | A few enhancements for optimizing user experience | ReadyForBuild |  | Sprint 7.3 | Yes